## Sheet1
Change | Driven by feedback | Result
Removed "Number of Support Options" from blue call to action button on hompage | Customers found it confusing. (Aug 22nd 2019 testing). The number is the total of Products/Services & Events. This is not easy for people to quickly grasp and was adding no real benefit. | Confusion mitigated :-)
Event Tab added to the listings page | Customers expressed confusion when events were mixed through the service listings. Events will massively outnumber Services and so hide them. | Research showed that this was well received and understood by users as a common pattern of delivery that they understood
Filters on changed to Sparate SEARCH and FILTEr sections in Left Hand sidebar. | Customers were confused by the mixing of Search(More results) and Filter(Less Results) options. These have now been separated visually on the side bar. | There is no longer that confusion between the two BUT There is still an outsstanding issue around Search being "OR" and not "AND" for certain people.
Categories... | BUT
Event Categories
Location...
Questions | Driven by feedback | Why we have not come to a decision yet
Query around removal of Content Links at the top of Service Descriptions | Customers on pages with sparse content, often viewed them as a unnecessary. Customers on pages with more lengthy content thought found them to be beneficial. | 1. More research required. 2. Actively investigating technological solutions on how to show only links on longer pages. 3. Not an issue for Alpha.
Should we add Search to the homepage | Customers have repeatedly expressed the need for a Search option on teh home page | 1. More research required.